## Sheet1
2016 | [8 empty] | 2017 | [11 empty] | 2018
Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May
Launch event |  | 6 ETRMA |  | 2 ITMA 4 Lizeo | 21 kick-off |  |  |  | 25 II meeting | 14 webconf
[7 empty] | Call for tenders |  | Lab selection & test planning
Market research winter tyres
Label inspection winter tyres
Doc inspection winter tyers
[8 empty] | Sampling winter tyres | Sampling winter tyres
[11 empty] | Testing winter tyres | [7 empty] | Repetition tests
[9 empty] | Market research summer tyres | [8 empty] | Delivery test reports summer tyres |  | Delivery TRs
Label inspection summer tyres
Doc inspection summer tyres
Sampling summer tyres
[15 empty] | Testing summer tyres |  |  |  | Repetition tests
[11 empty] | 28: III meeting for test planning in the laboratory | [6 empty] | Delivery test reports winter tyres |  | Delivery TRs | 10: IV meeting for analysis of test results |  |  | 12: V meeting for overall analysis | 30: final workshop MSTYR 15
[14 empty] | Enforcement actions for labels a nd documentation | [5 empty] | Enforcement actions for tests and for overall JA